## Initial Scope
Remi Pearson Website — Initial Scope
Baseline brief as of 19 Sep 2026 (from docs/Remi-Website-Progress.docx), and where each item landed on the live site.
# | Requirement (initial brief) | Source / design reference | Planned at baseline (19 Sep 2026) | Status at go-live | Delivered at (live URL) | Notes
Pages
1 | Home page: hero variants, rabbit holes, perspectives, products, enquiry form | v1.0 / v2.0 design canvas; NEW HOME PAGE PART ONE–TWO | Single static page with hero variants (A–D) | Done | https://www.remipearson.com/ | Rebuilt from the new homepage design; adds the Spotlight carousel. Homepage part three (about snapshot, newsletter band, "Fancy a proper conversation") not built yet.
2 | About Remi | Design screenshots 19–22 | Inner page | Done | https://www.remipearson.com/about-remi | Plus awards marquee and links into models, articles and rabbit holes.
3 | Invite Remi | Design screenshots 23–25 | Inner page with invitation form | Done | https://www.remipearson.com/invite-remi | Plus speaker reel (Vimeo) and TV & radio (Broadcast) option.
4 | Perspectives (podcast) | Design screenshots 26–29 | Inner page | Done | https://www.remipearson.com/perspectives | Searchable episode archive with topic filters, YouTube links, "Ask Remi" form.
5 | Ideas & Models | Ideas & Models PDF | One long overview page | Done — expanded | https://www.remipearson.com/ideas-models | Expanded into 10 chapter pages plus the CAM Mini Profiler (see Delivered sheet).
6 | T.R.U.S.T.M.E. page | Copy deck | Standalone page | Done — moved | https://www.remipearson.com/ideas-models/trustme-model | Now a chapter of Ideas & Models.
Site chrome
7 | Header navigation | v2.0 design | Top-level links | Done — expanded | https://www.remipearson.com/ | Drop-down menus (Books, Ideas & Models chapters, programs), site search (Ctrl/⌘ K).
8 | Footer | v2.0 design | Links + newsletter | Done | https://www.remipearson.com/ | Newsletter sign-up live through Resend; Privacy Policy link.
9 | "Talk to Remi" chat widget | v2.0 design | Scripted chat | Done | https://www.remipearson.com/ | Scripted keyword replies that hand off to the enquiry / invite forms.
Platform
10 | Hosting | — | Static export on Netlify | Changed | https://www.remipearson.com | Moved to Next.js on Vercel so the site can run server routes (forms, payments, votes).
11 | Forms | — | Stub (no sending) | Done — live | https://www.remipearson.com/#contact | All forms send through Resend with team notifications, auto-replies and mailing-list segments.
12 | Payments | — | None | Added | https://www.remipearson.com/books | Stripe Checkout for the three ebooks with emailed private download links.
13 | API routes | — | 0 | Added — 6 | https://www.remipearson.com | /api/lead, /api/helpful, /api/books/checkout, /webhook, /download, /resend (plus the private /stats page).
Baseline vs go-live at a glance
| Measure | Baseline (19 Sep 2026) | At go-live (Oct 2026)
| Pages in scope | 6 | 6
| Live pages in sitemap | 6
| Designed sales / waitlist pages | 0
| Free articles | 0
| Integrations | 0
| Hosting | Netlify (static) | Vercel (Next.js)
| Forms | Stub | Live — Resend
| Payments | None | Stripe (ebooks)

## Delivered
Remi Pearson Website — Delivered (Live)
Every live page on https://www.remipearson.com as listed in the sitemap at go-live (Oct 2026), plus integrations. Click a URL to open the page.
# | Area | Live URL | Page | What was delivered | Forms & integrations on the page | Status
Core pages
1 | Core page | https://www.remipearson.com | Remi Pearson — Let truth lead | Hero (variant C2 default, 6 variants), Spotlight carousel (Invite Remi, CAM for Leaders, reviews, weekly article, Selling from Stage, newsletter), "Which rabbit hole" cards, featured conversations, entry products, enquiry form. | Enquiry form (Resend + auto-reply); Vimeo hero video; chat widget | Live
2 | Core page | https://www.remipearson.com/about-remi | About Remi | Story, awards marquee, four model cards, "I know…" notes, life's work brand mark; built from screenshots 19–22. | Links to articles, chapters, speaker reel | Live
3 | Core page | https://www.remipearson.com/invite-remi | Invite Remi | Formats (incl. TV & radio), speaker reel, invitation form; built from screenshots 23–25. | Invitation form (Resend + auto-reply, "Invite Remi" segment); Vimeo reel | Live
4 | Core page | https://www.remipearson.com/perspectives | Perspectives | Places to begin, featured episodes, searchable archive with topic filters, rabbit-hole strips, "Remi as guest". | YouTube episode links; "Ask Remi" private form (Resend) | Live
5 | Core page | https://www.remipearson.com/reviews | Reviews: What People Say About Learning with Remi Pearson | 34 testimonials, featured review band, filter chips, balanced columns. | Feeds homepage Spotlight reviews slide | Live
6 | Core page | https://www.remipearson.com/subscribe | Let Truth Lead: Free Fortnightly Newsletter | Let Truth Lead newsletter page from the copy deck and mockup. | Two sign-up forms → Resend newsletter list | Live
7 | Core page | https://www.remipearson.com/privacy-policy | Privacy Policy | Privacy policy (footer link). | — | Live
Ideas & Models
8 | Ideas & Models | https://www.remipearson.com/ideas-models | Ideas & Models | Full overview from the PDF: glance index, 8 parts, hand-drawn diagrams, tap-to-enlarge on phones. | Links to every chapter | Live
9 | Ideas & Models chapter | https://www.remipearson.com/ideas-models/self-esteem-triad | How Do You Build Self-Esteem That Lasts? The Self-Esteem Triad | Chapter from copy deck, hero diagram, CTA to the Triad sales page. | "Tell me when it's ready" form until product link set | Live
10 | Ideas & Models chapter | https://www.remipearson.com/ideas-models/safe-problems-risky-truths | Why Do We Keep Trying to Solve the Same Problem? Safe Problems, Risky Truths | Chapter from copy deck with posters. | — | Live
11 | Ideas & Models chapter | https://www.remipearson.com/ideas-models/deep-state-repatterning | Why Does the Past Still Affect You When You Know It’s Over? Deep State Repatterning | Chapter from copy deck with the pearls and emotions diagrams. | — | Live
12 | Ideas & Models chapter | https://www.remipearson.com/ideas-models/emotion-integration-technique | Why Can’t I Feel My Emotions Even When I Understand Myself? Emotion Integration Technique | Chapter from copy deck with the tree diagram; practitioner training button. | Enquiry form link | Live
13 | Ideas & Models chapter | https://www.remipearson.com/ideas-models/values-alignment-technique | Values Alignment Technique | Chapter from copy deck with the reveals / protection diagrams. | Enquiry form link | Live
14 | Ideas & Models chapter | https://www.remipearson.com/ideas-models/critical-alignment-model | The Critical Alignment Model | Chapter with CAM hero illustration and "Work with the model" buttons. | Links: Rebel Yell waitlist, Mini Profiler, book | Live
15 | Ideas & Models chapter | https://www.remipearson.com/ideas-models/critical-alignment-model/mini-profiler | The CAM Mini Profiler | CAM Mini Profiler landing page (3 parts, compass wheel, four dimensions). | "Access the assessment" → enquiry form until quiz link | Live
16 | Ideas & Models chapter | https://www.remipearson.com/ideas-models/trustme-model | The T.R.U.S.T.M.E. Model | T.R.U.S.T.M.E. spiral, seven levels, "Work with Remi" buttons. | Invite form (Facilitation), waitlist links | Live
17 | Ideas & Models chapter | https://www.remipearson.com/ideas-models/disruptive-leadership | Disruptive Leadership | Five-movement cycle diagram and practices. | Book, Rebel Yell, invite links | Live
18 | Ideas & Models chapter | https://www.remipearson.com/ideas-models/first-90-days | Your First 90 Days as a Leader | Timeline poster, three phases, leadership tools. | Invite form (Consulting) | Live
19 | Ideas & Models chapter | https://www.remipearson.com/ideas-models/ultimate-influence | Consultative Sales: How to Know When You and a Buyer Are the Right Match | Eight steps as linked stones with anchor links. | Training button → enquiry form | Live
Rabbit-hole pages
20 | Rabbit hole | https://www.remipearson.com/i-know-better | I Know Better. Why Do I Still Keep Doing This? | Designs 1–3: pattern boxes, product block, other holes, newsletter band. | Newsletter band (Resend) | Live
21 | Rabbit hole | https://www.remipearson.com/loving-someone | Why Does Loving Someone Bring All My Shit to the Surface? | Designs 4–6: inline SVG cycle diagram, patterns, relationships links. | Newsletter band (Resend) | Live
22 | Rabbit hole | https://www.remipearson.com/tell-me-the-truth | Tell Me the Truth. What Am I Not Seeing? | Designs 7–9: four questions to the CAM chapter, conversations by topic. | Newsletter band (Resend) | Live
23 | Rabbit hole | https://www.remipearson.com/leadership | How Do I Lead Without Carrying Everybody? | Designs 10–12: T.R.U.S.T.M.E. block stack, links to chapters. | Newsletter band (Resend) | Live
24 | Rabbit hole | https://www.remipearson.com/ultimate-influence | How Do I Sell Without Scripts, Pressure or Bullshit? Ultimate Influence | Designs 13–15: transcribed copy, influence product range. | Newsletter band (Resend) | Live
25 | Rabbit hole | https://www.remipearson.com/build-an-asset | I’ve Built Myself a Job. How Do I Build an Asset? | Designs 16–18: T.R.U.S.T.M.E. timeline, Build Beyond the Founder bundle. | Newsletter band (Resend) | Live
Programs
26 | Programs | https://www.remipearson.com/programs | Programs | "Where shall we begin?" summary: free ways in, four programs as photo bands, category tiles. | — | Live
27 | Programs | https://www.remipearson.com/programs/rebel-yell | Rebel Yell | Full program page from the copy deck: bands, FAQ, private waitlist. | Waitlist form → Resend "Rebel Yell" segment | Live
28 | Programs | https://www.remipearson.com/programs/the-shift | The Shift | Placeholder program page. | Waitlist form → Resend (team email + product segment) | Live — coming soon
Programs & products
29 | Products | https://www.remipearson.com/products | Programs & products | Every self-paced range as designed photo bands, prices and levels from the sales summary. | — | Live
30 | Product — sales page | https://www.remipearson.com/products/self-esteem-triad | The Self-Esteem Triad | Designed page from Remi's copy deck and mockup. Six-part design, copy word for word. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
31 | Product — sales page | https://www.remipearson.com/products/becoming-conscious | Becoming Conscious: A Gentle Introduction to Presence | Designed page from Remi's copy deck and mockup. Three videos as photo rows, ringed icons. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
32 | Product — sales page | https://www.remipearson.com/products/self-regulation-when-it-matters | Self-Regulation When It Matters | Designed page from Remi's copy deck and mockup. Three-page mockup, five videos, workbook, meditation card. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
33 | Product — sales page | https://www.remipearson.com/products/deep-state-repatterning | Deep State Repatterning™ | Designed page from Remi's copy deck and mockup. Espresso bands, gold timeline of five videos, pearls diagram. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
34 | Product — sales page | https://www.remipearson.com/products/emotion-integration-technique-foundations | Emotion Integration Technique (EIT) Foundations | Designed page from Remi's copy deck and mockup. Burgundy bands with SVG sprigs, demonstration preview. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
35 | Product — sales page | https://www.remipearson.com/products/five-paths-to-a-healthy-relationship | The Five Paths to a Healthy Relationship | Designed page from Remi's copy deck and mockup. Five paths as numbered photo rows, Gottman band, worksheet. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
36 | Product — sales page | https://www.remipearson.com/products/finding-our-way-back | Finding Our Way Back: Repair After Conflict | Designed page from Remi's copy deck and mockup. Three videos with example phrases, workbook band (renamed from Conflict, Repair and Harmony). | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
37 | Product — sales page | https://www.remipearson.com/products/holding-space-without-rescuing-or-disappearing | Holding Space Without Rescuing or Disappearing | Designed page from Remi's copy deck and mockup. Five videos as alternating rows, three practices, FAQ. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
38 | Product — sales page | https://www.remipearson.com/products/obstacles-to-love | Obstacles to Love: Why You Keep Ending Up Hurt, Guarded or Alone | Designed page from Remi's copy deck and mockup. Seven videos with explore / cost / take-away lines, "Where next" products. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
39 | Product — sales page | https://www.remipearson.com/products/the-performance-management-blueprint | The Performance Management Blueprint | Designed page from Remi's copy deck and mockup. Four lessons, team band, workbook. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
40 | Product — sales page | https://www.remipearson.com/products/the-90-day-review | The 90-Day Review & Personal Success Plan | Designed page from Remi's copy deck and mockup. Waitlist page, no price shown until launch. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
41 | Product — sales page | https://www.remipearson.com/products/benchmarking-what-good-actually-looks-like | Benchmarking: What Good Actually Looks Like | Designed page from Remi's copy deck and mockup. One-page mockup, lead / lag section. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
42 | Product — sales page | https://www.remipearson.com/products/ultimate-influence-consultative-sales-introduction | Ultimate Influence: Consultative Sales Training | Designed page from Remi's copy deck and mockup. Complete eight-step methodology; price + GST worked out. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
43 | Product — sales page | https://www.remipearson.com/products/ultimate-influence-foundations | Ultimate Influence Foundations: Consultative Sales Introduction | Designed page from Remi's copy deck and mockup. Introductory product, separate from the full program. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
44 | Product — sales page | https://www.remipearson.com/products/selling-from-stage | Selling from Stage: The Eight-Step Pitch Method | Designed page from Remi's copy deck and mockup. Full online program ($1,997): 13 lessons with drawings, two bonuses, guarantee. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
45 | Product — sales page | https://www.remipearson.com/products/selling-from-stage-fundamentals | Selling from Stage Fundamentals: The Eight-Step Pitch | Designed page from Remi's copy deck and mockup. Three-video mini course ($79), opened by the homepage Spotlight. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
46 | Product — sales page | https://www.remipearson.com/products/from-practice-to-enterprise | Technician to Entrepreneur: Build a Business Beyond You | Designed page from Remi's copy deck and mockup. Technician to Entrepreneur: modules, story band figures. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
47 | Product — sales page | https://www.remipearson.com/products/trust-that-holds | Trust That Holds: The T.R.U.S.T.M.E. Program | Designed page from Remi's copy deck and mockup. T.R.U.S.T.M.E. program with two real testimonials. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
48 | Product — sales page | https://www.remipearson.com/products/critical-alignment-model-for-leaders | Critical Alignment Model for Leaders | Designed page from Remi's copy deck and mockup. Seven-part mockup, nine videos, price + GST, links to the Mini Profiler. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
49 | Bundle — sales page | https://www.remipearson.com/products/come-back-to-yourself | Come Back to Yourself: Five Self-Paced Programs | Designed page from Remi's copy deck and mockup. Five-program bundle; combined price and saving worked out from the catalogue. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
50 | Bundle — sales page | https://www.remipearson.com/products/build-beyond-the-founder | Build Beyond the Founder: Three Programs for Business Owners | Designed page from Remi's copy deck and mockup. Business bundle, $129 struck through beside $97. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
51 | Free series | https://www.remipearson.com/products/why-do-i-keep-doing-this | Why Do I Keep Doing This? Free Video Series | Designed page from Remi's copy deck and mockup. Registration page for five free videos; burgundy portrait hero. | Registration form → Resend free-series segment (marketing opt-in) | Live
52 | Free series | https://www.remipearson.com/products/attachment-or-love | Attachment or Love? Free Three-Video Series | Designed page from Remi's copy deck and mockup. Registration page for three free videos, three forms. | Registration form → Resend free-series segment (marketing opt-in) | Live
53 | Free program | https://www.remipearson.com/products/disruptive-leadership | Disruptive Leadership: Free Introductory Program | Designed page from Remi's copy deck and mockup. Free introductory leadership program, Four Pillars table. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
54 | Free program | https://www.remipearson.com/products/holding-space-for-magnetic-sales | Holding Space for Magnetic Sales: Free Sales Introduction | Designed page from Remi's copy deck and mockup. Free sales introduction drawn from Ultimate Influence. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
55 | Free program | https://www.remipearson.com/products/core-improve-innovate | Core, Improve, Innovate: Free Program for Business Owners | Designed page from Remi's copy deck and mockup. Free program for business owners; figures strip. | Waitlist form → Resend (team email + product segment) | Live — waitlist until checkout link is added
56 | Product — catalogue page | https://www.remipearson.com/products/love-without-losing-yourself | Love Without Losing Yourself | Catalogue product page: title, summary, price, level, included programs. Sales copy still to come. | Enquiry / notify link | Live — awaiting sales copy
57 | Product — catalogue page | https://www.remipearson.com/products/find-the-gap-in-your-own-life | Find the Gap in Your Own Life | Catalogue product page: title, summary, price, level. Sales copy still to come. | Enquiry / notify link | Live — awaiting sales copy
58 | Product — catalogue page | https://www.remipearson.com/products/when-your-values-and-your-life-stop-matching | When Your Values and Your Life Stop Matching | Catalogue product page: title, summary, price, level. Sales copy still to come. | Enquiry / notify link | Live — awaiting sales copy
59 | Product — catalogue page | https://www.remipearson.com/products/safe-or-risky-problems | Safe or Risky Problems? | Catalogue product page: title, summary, price, level. Sales copy still to come. | Enquiry / notify link | Live — awaiting sales copy
60 | Product — catalogue page | https://www.remipearson.com/products/let-truth-lead | Let Truth Lead | Catalogue product page: title, summary, price, level. Sales copy still to come. | Enquiry / notify link | Live — awaiting sales copy
61 | Product — catalogue page | https://www.remipearson.com/products/find-the-truth-of-the-situation | Find the Truth of the Situation | Catalogue product page: title, summary, price, level, included programs. Sales copy still to come. | Enquiry / notify link | Live — awaiting sales copy
62 | Product — catalogue page | https://www.remipearson.com/products/your-first-90-days-as-a-leader | Your First 90 Days as a Leader | Catalogue product page: title, summary, price, level. Sales copy still to come. | Enquiry / notify link | Live — awaiting sales copy
63 | Product — catalogue page | https://www.remipearson.com/products/the-ground-rules-nobody-wrote-down | The Ground Rules Nobody Wrote Down | Catalogue product page: title, summary, price, level. Sales copy still to come. | Enquiry / notify link | Live — awaiting sales copy
64 | Product — catalogue page | https://www.remipearson.com/products/lead-align-and-perform | Lead, Align and Perform | Catalogue product page: title, summary, price, level, included programs. Sales copy still to come. | Enquiry / notify link | Live — awaiting sales copy
65 | Product — catalogue page | https://www.remipearson.com/products/influence-without-pressure | Influence Without Pressure | Catalogue product page: title, summary, price, level, included programs. Sales copy still to come. | Enquiry / notify link | Live — awaiting sales copy
66 | Product — catalogue page | https://www.remipearson.com/products/untriggerable | Untriggerable | Catalogue product page: title, summary, price, level. Sales copy still to come. | Enquiry / notify link | Live — awaiting sales copy
Books & ebook sales
67 | Books | https://www.remipearson.com/books | Books | Three full-width book cards with sales copy, covers and prices. | Stripe "Buy" buttons | Live — selling
68 | Books | https://www.remipearson.com/books/disruptive-leadership | Disruptive Leadership by Remi Pearson — Ebook | Designed book page from the DL mockup. | Stripe Checkout (AUD $14.95) → emailed download link | Live — selling
69 | Books | https://www.remipearson.com/books/ultimate-you | Ultimate You by Remi Pearson — Ebook | Designed book page from the Ultimate You mockup. | Stripe Checkout (AUD $14.95) → emailed download link | Live — selling
70 | Books | https://www.remipearson.com/books/ultimate-you-quest | Ultimate You Quest Edition by Remi Pearson — Ebook | Designed book page from the Quest Edition mockup. | Stripe Checkout (AUD $24.95) → emailed download link | Live — selling
Free resources (articles)
71 | Free resources | https://www.remipearson.com/articles | Free resources | Free library in four topic clusters with framed card images. | — | Live
72 | Article | https://www.remipearson.com/articles/why-insight-isnt-enough | Why Do I Keep Repeating the Same Patterns Even When I Understand Myself? | Why insight isn’t enough, and what inner work makes possible. | "Was this helpful?" votes (Redis), share buttons, "Ask Remi" form, list sign-up (Resend) | Live
73 | Article | https://www.remipearson.com/articles/the-moment-you-leave-yourself | Why Do I Lose Myself in Relationships? | The moment you leave yourself, and how compassionate inner work helps you return. | "Was this helpful?" votes (Redis), share buttons, "Ask Remi" form, list sign-up (Resend) | Live
74 | Article | https://www.remipearson.com/articles/why-relationships-trigger-me | Why Do Relationships Trigger Me So Much? | Why loving someone brings old patterns to the surface, and how we begin responding differently. | "Was this helpful?" votes (Redis), share buttons, "Ask Remi" form, list sign-up (Resend) | Live
75 | Article | https://www.remipearson.com/articles/why-do-i-keep-repeating-the-same-patterns | Why Do I Keep Repeating the Same Patterns? | Tell me the truth … what am I missing? | "Was this helpful?" votes (Redis), share buttons, "Ask Remi" form, list sign-up (Resend) | Live
76 | Article | https://www.remipearson.com/articles/how-do-i-stop-micromanaging-my-team | How Do I Stop Micromanaging My Team? | How to lead without carrying everybody, using the Critical Alignment Model. | "Was this helpful?" votes (Redis), share buttons, "Ask Remi" form, list sign-up (Resend) | Live
77 | Article | https://www.remipearson.com/articles/build-a-business-that-runs-without-you | How Do You Build a Business That Can Run Without You? | How I went from coaching clients to building The Coaching Institute, and what replacing myself actually involved. | "Was this helpful?" votes (Redis), share buttons, "Ask Remi" form, list sign-up (Resend) | Live
78 | Article | https://www.remipearson.com/articles/find-the-root-cause-of-problems-in-your-business | How Do I Find the Root Cause of Problems in My Business? | Using the Critical Alignment Model to make better decisions, develop your team and close the gap between intention and results. | "Was this helpful?" votes (Redis), share buttons, "Ask Remi" form, list sign-up (Resend) | Live
79 | Article | https://www.remipearson.com/articles/why-leaders-revert-to-old-habits-under-pressure | Why Do Leaders Revert to Old Habits Under Pressure? | The T.R.U.S.T.M.E. model by Remi Pearson: seven ways of thinking that shape leadership, team culture and change. | "Was this helpful?" votes (Redis), share buttons, "Ask Remi" form, list sign-up (Resend) | Live
80 | Article | https://www.remipearson.com/articles/how-to-sell-without-being-pushy | How Do I Sell Without Being Pushy? | Consultative sales using the eight steps of Remi Pearson’s Ultimate Influence method. | "Was this helpful?" votes (Redis), share buttons, "Ask Remi" form, list sign-up (Resend) | Live
81 | Article | https://www.remipearson.com/articles/how-do-i-build-a-business-that-runs-without-me | How Do I Build a Business That Runs Without Me? | How I replaced myself through documented systems, deliberate team development and a culture people wanted to contribute to. | "Was this helpful?" votes (Redis), share buttons, "Ask Remi" form, list sign-up (Resend) | Live
82 | Article | https://www.remipearson.com/articles/how-do-i-make-sense-of-suffering | How Do I Make Sense of Suffering Without Forcing a Positive Spin? | A reflection on what has been lost, what you need now and what still matters, without turning pain into a lesson. | "Was this helpful?" votes (Redis), share buttons, "Ask Remi" form, list sign-up (Resend) | Live
83 | Article | https://www.remipearson.com/articles/how-to-support-someone-you-love | How to Support Someone You Love Without Losing Yourself | Holding space: how to listen with care, keep responsibility clear and make room for both people. | "Was this helpful?" votes (Redis), share buttons, "Ask Remi" form, list sign-up (Resend) | Live
84 | Article | https://www.remipearson.com/articles/how-do-i-solve-the-right-problem | How Do I Solve the Right Problem Instead of Staying Busy Fixing the Wrong One? | A practical way to investigate a recurring problem, make a clearer decision and turn it into work someone can own. | "Was this helpful?" votes (Redis), share buttons, "Ask Remi" form, list sign-up (Resend) | Live
85 | Article | https://www.remipearson.com/articles/what-are-emotional-bids | What Are Emotional Bids? How Small Moments Build Connection | How to recognise the small invitations through which we seek connection, and respond without becoming endlessly available. | "Was this helpful?" votes (Redis), share buttons, "Ask Remi" form, list sign-up (Resend) | Live
86 | Article | https://www.remipearson.com/articles/how-to-set-boundaries-without-feeling-guilty | How to Set Boundaries Without Feeling Guilty | What guilt can tell you, the six kinds of boundary, and how to hold a limit while staying connected. | "Was this helpful?" votes (Redis), share buttons, "Ask Remi" form, list sign-up (Resend) | Live
87 | Article | https://www.remipearson.com/articles/why-dont-i-feel-good-enough | Why Don’t I Feel Good Enough, No Matter What I Achieve? | Why achievement can leave the feeling of being insufficient untouched, and seven ways to come back to yourself. | "Was this helpful?" votes (Redis), share buttons, "Ask Remi" form, list sign-up (Resend) | Live
88 | Article | https://www.remipearson.com/articles/why-do-i-never-have-enough-time | Why Do I Never Have Enough Time, Even When I’m Productive? | How to tell an overloaded life from a planning problem, and make more deliberate choices about what your time is for. | "Was this helpful?" votes (Redis), share buttons, "Ask Remi" form, list sign-up (Resend) | Live
89 | Article | https://www.remipearson.com/articles/how-to-reconnect-after-conflict | How to Reconnect After Conflict: Harmony, Disharmony and Repair | How relationships move through harmony, disharmony and repair, and how to find your way back with honesty, responsibility and care. | "Was this helpful?" votes (Redis), share buttons, "Ask Remi" form, list sign-up (Resend) | Live
90 | Article | https://www.remipearson.com/articles/how-to-stop-overthinking | How to Stop Overthinking and Trust Yourself | How to tell useful reflection from a loop that leaves you more distressed and no better informed, and how to step back into your life. | "Was this helpful?" votes (Redis), share buttons, "Ask Remi" form, list sign-up (Resend) | Live
91 | Article | https://www.remipearson.com/articles/how-do-i-find-meaning-in-life | How Do I Find Meaning in Life When Everything Feels Pointless? | What feels absent, whose priorities you are living by, and how to give what matters a place in your actual life. | "Was this helpful?" votes (Redis), share buttons, "Ask Remi" form, list sign-up (Resend) | Live
92 | Article | https://www.remipearson.com/articles/what-is-my-attachment-style | What Is My Attachment Style? Understanding How You Connect in Relationships | What happens inside you, and between you, when connection matters, and how to begin changing a pattern that costs you the relationship you want. | "Was this helpful?" votes (Redis), share buttons, "Ask Remi" form, list sign-up (Resend) | Live
93 | Article | https://www.remipearson.com/articles/how-to-overcome-fear-of-failure | How to Overcome Fear of Failure and Find the Courage to Live Fully | How courage works, how to build your capacity for uncertainty and how a meaningful purpose can carry you when confidence is nowhere to be found. | "Was this helpful?" votes (Redis), share buttons, "Ask Remi" form, list sign-up (Resend) | Live
Private pages & API endpoints (not in the sitemap)
94 | Private page | https://www.remipearson.com/books/thank-you | Book thank-you page | Where Stripe returns a buyer: confirms the paid order and shows the download buttons straight away. Noindex. | Stripe (reads the order back) | Live
95 | Private page | https://www.remipearson.com/stats?key=… | Helpful-vote stats | Team-only totals of "Was this helpful?" votes for every article. Needs STATS_KEY. Noindex. | Upstash Redis | Live
96 | API | https://www.remipearson.com/api/lead | Lead endpoint | Single endpoint for every form: enquiries, invitations, waitlists, sign-ups, feedback. Honeypot spam trap. | Resend (email + contacts/segments) | Live
97 | API | https://www.remipearson.com/api/helpful | Helpful votes | Counts article votes, one per connection per article per day. | Upstash Redis | Live
98 | API | https://www.remipearson.com/api/books/checkout | Book checkout | Opens Stripe Checkout at the price set on the server (not the browser). | Stripe | Live
99 | API | https://www.remipearson.com/api/books/webhook | Stripe webhook | Verifies Stripe's signature, re-reads the order from Stripe, emails the buyer once per order. | Stripe + Resend + Redis | Live
100 | API | https://www.remipearson.com/api/books/download | Book download | Checks the signed 7-day link, then redirects to a 10-minute private file URL. | Vercel Blob (private) | Live
101 | API | https://www.remipearson.com/api/books/resend?key=…&order=cs_… | Resend book link | Team tool: emails a buyer a fresh 7-day link. Needs STATS_KEY. | Stripe + Resend | Live
102 | Generated | https://www.remipearson.com/sitemap.xml | Sitemap | Generated each build: every page, article dates, book and article images. | — | Live
103 | Generated | https://www.remipearson.com/robots.txt | Robots | Allows everything except /api/. | — | Live
104 | Generated | https://www.remipearson.com/llms.txt | llms.txt | Page titles and descriptions for AI search tools, generated from the sitemap. | — | Live
Integrations & site-wide features
105 | Integration | Stripe | Ebook payments | Stripe Checkout for the three ebooks (AUD, price set on the server). Webhook verified by signature; order re-read from Stripe and only delivered when paid. Buyer gets an emailed download link signed with a secret (HMAC), valid 7 days; files sit in private storage and are served by 10-minute signed URLs. Team can resend a link. | STRIPE_SECRET_KEY, STRIPE_WEBHOOK_SECRET, BOOKS_DOWNLOAD_SECRET | Live
106 | Integration | Resend — email | Form notifications & auto-replies | Every form posts to /api/lead: the team gets a notification titled by that form's topic (product, list, interest or page); enquiries and invitations get an automatic reply; book buyers get their download email and the team a "Book sale" notice. | RESEND_API_KEY, RESEND_FROM, RESEND_TO | Live
107 | Integration | Resend — contacts | Mailing-list segments | Sign-ups, waitlists and invitations become Resend contacts sorted into segments, created automatically by name: topic lists (Leadership, Business, Personal development, Consultative sales, Relationships), Invite Remi, product waitlists and free series. Free-series marketing only with an opt-in tick. | RESEND_SEGMENT_ID (+ optional per-list overrides) | Live
108 | Integration | Forms on the site | Enquiry, invite, newsletter, waitlist, feedback | Homepage enquiry, Invite Remi, footer + /subscribe newsletter, Rebel Yell and product waitlists, free-series registrations, "Ask Remi" on articles and Perspectives, topic list sign-ups. Buttons disable while sending, errors are shown, hidden honeypot drops spam. Links can preset the form (?interest= / ?invite=). | submitLead → /api/lead | Live
109 | Integration | Upstash Redis | Votes & delivery tracking | "Was this helpful?" votes and counts on every article; "N readers found this helpful"; once-per-order book delivery. | KV_REST_API_URL, KV_REST_API_TOKEN | Live
110 | Integration | Vercel Blob (private) | Ebook file storage | The three ebook PDFs stored privately (anonymous access refused); uploaded with npm run upload-books. | BLOB_READ_WRITE_TOKEN | Live
111 | Integration | Vercel | Hosting & deploys | Next.js App Router on Vercel: prerendered pages, server API routes, homepage revalidates hourly (weekly article rotates without a deploy). | — | Live
112 | Integration | Vimeo / YouTube | Video | Vimeo hero video and speaker reel (click to play); Perspectives episodes link to YouTube. | SITE.vimeoId, speakerReelVimeoId | Live
113 | Feature | Site search | Header search (Ctrl/⌘ K or /) | Index built automatically each build from every page heading; suggestion chips. | public/search-index.json | Live
114 | Feature | SEO & redirects | Search listings, sitemap, old URLs | Written search descriptions per page; generated sitemap, robots and llms.txt; redirects from old .html pages and the previous Wix site (/post/, /blog/, /about, /workwithremi…). | next.config.mjs | Live
115 | Feature | Reader tools | Share & feedback on articles | Share sheet, copy link, email, LinkedIn, Facebook, WhatsApp (no third-party scripts); share drop-down at the top of every article. | — | Live
116 | Feature | Chat widget | "Talk to Remi" | Scripted keyword replies on every page, handing off to the enquiry or invite form. | content/chat.ts | Live
117 | Feature | Smooth scrolling & UX | Site-wide | Eased scrolling (Lenis), pages open at the top, reduced-motion respected, phone layouts checked down to 320px. | — | Live
Summary
Live pages in sitemap
Designed sales / waitlist pages
Catalogue product pages (sales copy to come)
Articles
Ideas & Models chapters (incl. Mini Profiler)
Integrations