## Initial Scope
Remi Pearson Website — Initial Scope
Baseline brief as of 19 Sep 2026 (from docs/Remi-Website-Progress.docx), and where each item landed on the live site.
# | Requirement (initial brief) | Source / design reference | Planned at baseline (19 Sep 2026) | Status at go-live | Delivered at (live URL) | Notes
Pages
1 | Home page: hero variants, rabbit holes, perspectives, products, enquiry form | v1.0 / v2.0 design canvas; NEW HOME PAGE PART ONE–TWO | Single static page with hero variants (A–D) | Done | https://www.remipearson.com/ | Rebuilt from the new homepage design; adds the Spotlight carousel. Homepage part three (about snapshot, newsletter band, "Fancy a proper conversation") not built yet.
2 | About Remi | Design screenshots 19–22 | Inner page | Done | https://www.remipearson.com/about-remi | Plus awards marquee and links into models, articles and rabbit holes.
3 | Invite Remi | Design screenshots 23–25 | Inner page with invitation form | Done | https://www.remipearson.com/invite-remi | Plus speaker reel (Vimeo) and TV & radio (Broadcast) option.
4 | Perspectives (podcast) | Design screenshots 26–29 | Inner page | Done | https://www.remipearson.com/perspectives | Searchable episode archive with topic filters, YouTube links, "Ask Remi" form.
5 | Ideas & Models | Ideas & Models PDF | One long overview page | Done — expanded | https://www.remipearson.com/ideas-models | Expanded into 10 chapter pages plus the CAM Mini Profiler (see Delivered sheet).
6 | T.R.U.S.T.M.E. page | Copy deck | Standalone page | Done — moved | https://www.remipearson.com/ideas-models/trustme-model | Now a chapter of Ideas & Models.
Site chrome
7 | Header navigation | v2.0 design | Top-level links | Done — expanded | https://www.remipearson.com/ | Drop-down menus (Books, Ideas & Models chapters, programs), site search (Ctrl/⌘ K).
8 | Footer | v2.0 design | Links + newsletter | Done | https://www.remipearson.com/ | Newsletter sign-up live through Resend; Privacy Policy link.
9 | "Talk to Remi" chat widget | v2.0 design | Scripted chat | Done | https://www.remipearson.com/ | Scripted keyword replies that hand off to the enquiry / invite forms.
Baseline vs go-live at a glance
| Measure | Baseline (19 Sep 2026) | At go-live (Oct 2026)
| Pages in scope | 6 | 6
| Live pages in sitemap | 6 | 88
| Designed sales / waitlist pages | 0 | 26
| Free articles | 0 | 22
| Integrations | 0 | 6
| Hosting | Netlify (static) | Vercel (Next.js)
| Forms | Stub | Live — Resend
| Payments | None | Stripe (ebooks)

## After Delivery
Pages After Going Live
Every live page on https://www.remipearson.com as listed in the sitemap at go-live (Oct 2026), plus integrations. Click a URL to open the page.
# | Area | Live URL | Page | What was delivered | Status
Core pages
1 | Core page | https://www.remipearson.com/perspectives | Perspectives | Designed from Remi's mockup and info file from Drive | Live
2 | Core page | https://www.remipearson.com/reviews | Reviews: What People Say About Learning with Remi Pearson | Designed from Remi's mockup and info file from Drive | Live
3 | Core page | https://www.remipearson.com/subscribe | Let Truth Lead: Free Fortnightly Newsletter | Designed from Remi's mockup and info file from Drive | Live
4 | Core page | https://www.remipearson.com/privacy-policy | Privacy Policy | Privacy policy | Live
Ideas & Models
5 | Ideas & Models chapter | https://www.remipearson.com/ideas-models/self-esteem-triad | How Do You Build Self-Esteem That Lasts? The Self-Esteem Triad | Designed from Remi's mockup and info file from Drive | Live
6 | Ideas & Models chapter | https://www.remipearson.com/ideas-models/safe-problems-risky-truths | Why Do We Keep Trying to Solve the Same Problem? Safe Problems, Risky Truths | Designed from Remi's mockup and info file from Drive | Live
7 | Ideas & Models chapter | https://www.remipearson.com/ideas-models/deep-state-repatterning | Why Does the Past Still Affect You When You Know It’s Over? Deep State Repatterning | Designed from Remi's mockup and info file from Drive | Live
8 | Ideas & Models chapter | https://www.remipearson.com/ideas-models/emotion-integration-technique | Why Can’t I Feel My Emotions Even When I Understand Myself? Emotion Integration Technique | Designed from Remi's mockup and info file from Drive | Live
9 | Ideas & Models chapter | https://www.remipearson.com/ideas-models/values-alignment-technique | Values Alignment Technique | Designed from Remi's mockup and info file from Drive | Live
10 | Ideas & Models chapter | https://www.remipearson.com/ideas-models/critical-alignment-model | The Critical Alignment Model | Designed from Remi's mockup and info file from Drive | Live
11 | Ideas & Models chapter | https://www.remipearson.com/ideas-models/critical-alignment-model/mini-profiler | The CAM Mini Profiler | Designed from Remi's mockup and info file from Drive | Live
12 | Ideas & Models chapter | https://www.remipearson.com/ideas-models/disruptive-leadership | Disruptive Leadership | Designed from Remi's mockup and info file from Drive | Live
13 | Ideas & Models chapter | https://www.remipearson.com/ideas-models/first-90-days | Your First 90 Days as a Leader | Designed from Remi's mockup and info file from Drive | Live
14 | Ideas & Models chapter | https://www.remipearson.com/ideas-models/ultimate-influence | Consultative Sales: How to Know When You and a Buyer Are the Right Match | Designed from Remi's mockup and info file from Drive | Live
Rabbit-hole pages
15 | Rabbit hole | https://www.remipearson.com/i-know-better | I Know Better. Why Do I Still Keep Doing This? | Designed from Remi's mockup and info file from Drive | Live
16 | Rabbit hole | https://www.remipearson.com/loving-someone | Why Does Loving Someone Bring All My Shit to the Surface? | Designed from Remi's mockup and info file from Drive | Live
17 | Rabbit hole | https://www.remipearson.com/tell-me-the-truth | Tell Me the Truth. What Am I Not Seeing? | Designed from Remi's mockup and info file from Drive | Live
18 | Rabbit hole | https://www.remipearson.com/leadership | How Do I Lead Without Carrying Everybody? | Designed from Remi's mockup and info file from Drive | Live
19 | Rabbit hole | https://www.remipearson.com/ultimate-influence | How Do I Sell Without Scripts, Pressure or Bullshit? Ultimate Influence | Designed from Remi's mockup and info file from Drive | Live
20 | Rabbit hole | https://www.remipearson.com/build-an-asset | I’ve Built Myself a Job. How Do I Build an Asset? | Designed from Remi's mockup and info file from Drive | Live
Programs
21 | Programs | https://www.remipearson.com/programs | Programs | Designed from Remi's mockup and info file from Drive | Live
22 | Programs | https://www.remipearson.com/programs/rebel-yell | Rebel Yell | Designed from Remi's mockup and info file from Drive | Live
23 | Programs | https://www.remipearson.com/programs/the-shift | The Shift | Placeholder waiting for Remi | Placeholder Page
Programs & products
24 | Products | https://www.remipearson.com/products | Programs & products | Designed from Remi's mockup and info file from Drive | Live
25 | Product — sales page | https://www.remipearson.com/products/self-esteem-triad | The Self-Esteem Triad | Designed from Remi's mockup and info file from Drive | Live
26 | Product — sales page | https://www.remipearson.com/products/becoming-conscious | Becoming Conscious: A Gentle Introduction to Presence | Designed from Remi's mockup and info file from Drive | Live
27 | Product — sales page | https://www.remipearson.com/products/self-regulation-when-it-matters | Self-Regulation When It Matters | Designed from Remi's mockup and info file from Drive | Live
28 | Product — sales page | https://www.remipearson.com/products/deep-state-repatterning | Deep State Repatterning™ | Designed from Remi's mockup and info file from Drive | Live
29 | Product — sales page | https://www.remipearson.com/products/emotion-integration-technique-foundations | Emotion Integration Technique (EIT) Foundations | Designed from Remi's mockup and info file from Drive | Live
30 | Product — sales page | https://www.remipearson.com/products/five-paths-to-a-healthy-relationship | The Five Paths to a Healthy Relationship | Designed from Remi's mockup and info file from Drive | Live
31 | Product — sales page | https://www.remipearson.com/products/finding-our-way-back | Finding Our Way Back: Repair After Conflict | Designed from Remi's mockup and info file from Drive | Live
32 | Product — sales page | https://www.remipearson.com/products/holding-space-without-rescuing-or-disappearing | Holding Space Without Rescuing or Disappearing | Designed from Remi's mockup and info file from Drive | Live
33 | Product — sales page | https://www.remipearson.com/products/obstacles-to-love | Obstacles to Love: Why You Keep Ending Up Hurt, Guarded or Alone | Designed from Remi's mockup and info file from Drive | Live
34 | Product — sales page | https://www.remipearson.com/products/the-performance-management-blueprint | The Performance Management Blueprint | Designed from Remi's mockup and info file from Drive | Live
35 | Product — sales page | https://www.remipearson.com/products/the-90-day-review | The 90-Day Review & Personal Success Plan | Designed from Remi's mockup and info file from Drive | Live
36 | Product — sales page | https://www.remipearson.com/products/benchmarking-what-good-actually-looks-like | Benchmarking: What Good Actually Looks Like | Designed from Remi's mockup and info file from Drive | Live
37 | Product — sales page | https://www.remipearson.com/products/ultimate-influence-consultative-sales-introduction | Ultimate Influence: Consultative Sales Training | Designed from Remi's mockup and info file from Drive | Live
38 | Product — sales page | https://www.remipearson.com/products/ultimate-influence-foundations | Ultimate Influence Foundations: Consultative Sales Introduction | Designed from Remi's mockup and info file from Drive | Live
39 | Product — sales page | https://www.remipearson.com/products/selling-from-stage | Selling from Stage: The Eight-Step Pitch Method | Designed from Remi's mockup and info file from Drive | Live
40 | Product — sales page | https://www.remipearson.com/products/selling-from-stage-fundamentals | Selling from Stage Fundamentals: The Eight-Step Pitch | Designed from Remi's mockup and info file from Drive | Live
41 | Product — sales page | https://www.remipearson.com/products/from-practice-to-enterprise | Technician to Entrepreneur: Build a Business Beyond You | Designed from Remi's mockup and info file from Drive | Live
42 | Product — sales page | https://www.remipearson.com/products/trust-that-holds | Trust That Holds: The T.R.U.S.T.M.E. Program | Designed from Remi's mockup and info file from Drive | Live
43 | Product — sales page | https://www.remipearson.com/products/critical-alignment-model-for-leaders | Critical Alignment Model for Leaders | Designed from Remi's mockup and info file from Drive | Live
44 | Bundle — sales page | https://www.remipearson.com/products/come-back-to-yourself | Come Back to Yourself: Five Self-Paced Programs | Designed from Remi's mockup and info file from Drive | Live
45 | Bundle — sales page | https://www.remipearson.com/products/build-beyond-the-founder | Build Beyond the Founder: Three Programs for Business Owners | Designed from Remi's mockup and info file from Drive | Live
46 | Free series | https://www.remipearson.com/products/why-do-i-keep-doing-this | Why Do I Keep Doing This? Free Video Series | Designed from Remi's mockup and info file from Drive | Live
47 | Free series | https://www.remipearson.com/products/attachment-or-love | Attachment or Love? Free Three-Video Series | Designed from Remi's mockup and info file from Drive | Live
48 | Free program | https://www.remipearson.com/products/disruptive-leadership | Disruptive Leadership: Free Introductory Program | Designed from Remi's mockup and info file from Drive | Live
49 | Free program | https://www.remipearson.com/products/holding-space-for-magnetic-sales | Holding Space for Magnetic Sales: Free Sales Introduction | Designed from Remi's mockup and info file from Drive | Live
50 | Free program | https://www.remipearson.com/products/core-improve-innovate | Core, Improve, Innovate: Free Program for Business Owners | Designed from Remi's mockup and info file from Drive | Live
51 | Product — catalogue page | https://www.remipearson.com/products/love-without-losing-yourself | Love Without Losing Yourself | Placeholder waiting for Remi | Placeholder Page
52 | Product — catalogue page | https://www.remipearson.com/products/find-the-gap-in-your-own-life | Find the Gap in Your Own Life | Placeholder waiting for Remi | Placeholder Page
53 | Product — catalogue page | https://www.remipearson.com/products/when-your-values-and-your-life-stop-matching | When Your Values and Your Life Stop Matching | Placeholder waiting for Remi | Placeholder Page
54 | Product — catalogue page | https://www.remipearson.com/products/safe-or-risky-problems | Safe or Risky Problems? | Placeholder waiting for Remi | Placeholder Page
55 | Product — catalogue page | https://www.remipearson.com/products/let-truth-lead | Let Truth Lead | Placeholder waiting for Remi | Placeholder Page
56 | Product — catalogue page | https://www.remipearson.com/products/find-the-truth-of-the-situation | Find the Truth of the Situation | Placeholder waiting for Remi | Placeholder Page
57 | Product — catalogue page | https://www.remipearson.com/products/your-first-90-days-as-a-leader | Your First 90 Days as a Leader | Placeholder waiting for Remi | Placeholder Page
58 | Product — catalogue page | https://www.remipearson.com/products/the-ground-rules-nobody-wrote-down | The Ground Rules Nobody Wrote Down | Placeholder waiting for Remi | Placeholder Page
59 | Product — catalogue page | https://www.remipearson.com/products/lead-align-and-perform | Lead, Align and Perform | Placeholder waiting for Remi | Placeholder Page
60 | Product — catalogue page | https://www.remipearson.com/products/influence-without-pressure | Influence Without Pressure | Placeholder waiting for Remi | Placeholder Page
61 | Product — catalogue page | https://www.remipearson.com/products/untriggerable | Untriggerable | Placeholder waiting for Remi | Placeholder Page
Books & ebook sales
62 | Books | https://www.remipearson.com/books | Books | Designed from Remi's mockup and info file from Drive | Live
63 | Books | https://www.remipearson.com/books/disruptive-leadership | Disruptive Leadership by Remi Pearson — Ebook | Designed from Remi's mockup and info file from Drive | Live
64 | Books | https://www.remipearson.com/books/ultimate-you | Ultimate You by Remi Pearson — Ebook | Designed from Remi's mockup and info file from Drive | Live
65 | Books | https://www.remipearson.com/books/ultimate-you-quest | Ultimate You Quest Edition by Remi Pearson — Ebook | Designed from Remi's mockup and info file from Drive | Live
Free resources (articles)
66 | Free resources | https://www.remipearson.com/articles | Free resources | Designed from Remi's mockup and info file from Drive | Live
67 | Article | https://www.remipearson.com/articles/why-insight-isnt-enough | Why Do I Keep Repeating the Same Patterns Even When I Understand Myself? | Written from Remi's article file from Drive | Live
68 | Article | https://www.remipearson.com/articles/the-moment-you-leave-yourself | Why Do I Lose Myself in Relationships? | Written from Remi's article file from Drive | Live
69 | Article | https://www.remipearson.com/articles/why-relationships-trigger-me | Why Do Relationships Trigger Me So Much? | Written from Remi's article file from Drive | Live
70 | Article | https://www.remipearson.com/articles/why-do-i-keep-repeating-the-same-patterns | Why Do I Keep Repeating the Same Patterns? | Written from Remi's article file from Drive | Live
71 | Article | https://www.remipearson.com/articles/how-do-i-stop-micromanaging-my-team | How Do I Stop Micromanaging My Team? | Written from Remi's article file from Drive | Live
72 | Article | https://www.remipearson.com/articles/build-a-business-that-runs-without-you | How Do You Build a Business That Can Run Without You? | Written from Remi's article file from Drive | Live
73 | Article | https://www.remipearson.com/articles/find-the-root-cause-of-problems-in-your-business | How Do I Find the Root Cause of Problems in My Business? | Written from Remi's article file from Drive | Live
74 | Article | https://www.remipearson.com/articles/why-leaders-revert-to-old-habits-under-pressure | Why Do Leaders Revert to Old Habits Under Pressure? | Written from Remi's article file from Drive | Live
75 | Article | https://www.remipearson.com/articles/how-to-sell-without-being-pushy | How Do I Sell Without Being Pushy? | Written from Remi's article file from Drive | Live
76 | Article | https://www.remipearson.com/articles/how-do-i-build-a-business-that-runs-without-me | How Do I Build a Business That Runs Without Me? | Written from Remi's article file from Drive | Live
77 | Article | https://www.remipearson.com/articles/how-do-i-make-sense-of-suffering | How Do I Make Sense of Suffering Without Forcing a Positive Spin? | Written from Remi's article file from Drive | Live
78 | Article | https://www.remipearson.com/articles/how-to-support-someone-you-love | How to Support Someone You Love Without Losing Yourself | Written from Remi's article file from Drive | Live
79 | Article | https://www.remipearson.com/articles/how-do-i-solve-the-right-problem | How Do I Solve the Right Problem Instead of Staying Busy Fixing the Wrong One? | Written from Remi's article file from Drive | Live
80 | Article | https://www.remipearson.com/articles/what-are-emotional-bids | What Are Emotional Bids? How Small Moments Build Connection | Written from Remi's article file from Drive | Live
81 | Article | https://www.remipearson.com/articles/how-to-set-boundaries-without-feeling-guilty | How to Set Boundaries Without Feeling Guilty | Written from Remi's article file from Drive | Live
82 | Article | https://www.remipearson.com/articles/why-dont-i-feel-good-enough | Why Don’t I Feel Good Enough, No Matter What I Achieve? | Written from Remi's article file from Drive | Live
83 | Article | https://www.remipearson.com/articles/why-do-i-never-have-enough-time | Why Do I Never Have Enough Time, Even When I’m Productive? | Written from Remi's article file from Drive | Live
84 | Article | https://www.remipearson.com/articles/how-to-reconnect-after-conflict | How to Reconnect After Conflict: Harmony, Disharmony and Repair | Written from Remi's article file from Drive | Live
85 | Article | https://www.remipearson.com/articles/how-to-stop-overthinking | How to Stop Overthinking and Trust Yourself | Written from Remi's article file from Drive | Live
86 | Article | https://www.remipearson.com/articles/how-do-i-find-meaning-in-life | How Do I Find Meaning in Life When Everything Feels Pointless? | Written from Remi's article file from Drive | Live
87 | Article | https://www.remipearson.com/articles/what-is-my-attachment-style | What Is My Attachment Style? Understanding How You Connect in Relationships | Written from Remi's article file from Drive | Live
88 | Article | https://www.remipearson.com/articles/how-to-overcome-fear-of-failure | How to Overcome Fear of Failure and Find the Courage to Live Fully | Written from Remi's article file from Drive | Live
Summary
| Live pages in sitemap | 88
| Designed sales / waitlist pages | 26
| Placeholder pages | 12
| Articles | 22
| Ideas & Models chapters (incl. Mini Profiler) | 10
| Integrations (see Integrations sheet) | 6

## Integrations
Remi Pearson Website — Integrations & Site-wide Features
Third-party services and site-wide features running on https://www.remipearson.com at go-live (Oct 2026).
# | Type | Integration / feature | Purpose | What it does | Status
1 | Integration | Stripe | Ebook payments | Stripe Checkout for the three ebooks (AUD, price set on the server). Webhook verified by signature; order re-read from Stripe and only delivered when paid. Buyer gets an emailed download link signed with a secret (HMAC), valid 7 days; files sit in private storage and are served by 10-minute signed URLs. Team can resend a link. | Live
2 | Integration | Resend — email | Form notifications & auto-replies | Every form posts to /api/lead: the team gets a notification titled by that form's topic (product, list, interest or page); enquiries and invitations get an automatic reply; book buyers get their download email and the team a "Book sale" notice. | Live
3 | Integration | Resend — contacts | Mailing-list segments | Sign-ups, waitlists and invitations become Resend contacts sorted into segments, created automatically by name: topic lists (Leadership, Business, Personal development, Consultative sales, Relationships), Invite Remi, product waitlists and free series. Free-series marketing only with an opt-in tick. | Live
4 | Integration | Forms on the site | Enquiry, invite, newsletter, waitlist, feedback | Homepage enquiry, Invite Remi, footer + /subscribe newsletter, Rebel Yell and product waitlists, free-series registrations, "Ask Remi" on articles and Perspectives, topic list sign-ups. Buttons disable while sending, errors are shown, hidden honeypot drops spam. Links can preset the form (?interest= / ?invite=). | Live
5 | Integration | Upstash Redis | Votes & delivery tracking | "Was this helpful?" votes and counts on every article; "N readers found this helpful"; once-per-order book delivery. | Live
6 | Integration | Vercel Blob (private) | Ebook file storage | The three ebook PDFs stored privately (anonymous access refused); uploaded with npm run upload-books. | Live
7 | Feature | Site search | Header search (Ctrl/⌘ K or /) | Index built automatically each build from every page heading; suggestion chips. | Live
8 | Feature | SEO & redirects | Search listings, sitemap, old URLs | Written search descriptions per page; generated sitemap, robots and llms.txt; redirects from old .html pages and the previous Wix site (/post/, /blog/, /about, /workwithremi…). | Live
9 | Feature | Reader tools | Share & feedback on articles | Share sheet, copy link, email, LinkedIn, Facebook, WhatsApp (no third-party scripts); share drop-down at the top of every article. | Live
10 | Feature | Chat widget | "Talk to Remi" | Scripted keyword replies on every page, handing off to the enquiry or invite form. | Live